## T10_Layout
[5 empty] | 9月 | [29 empty] | 10月
[5 empty] | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10
[5 empty] | 46266 | 46267 | 46268 | 46269 | 46270 | 46271 | 46272 | 46273 | 46274 | 46275 | 46276 | 46277 | 46278 | 46279 | 46280 | 46281 | 46282 | 46283 | 46284 | 46285 | 46286 | 46287 | 46288 | 46289 | 46290 | 46291 | 46292 | 46293 | 46294 | 46295 | 46296 | 46297 | 46298 | 46299 | 46300 | 46301 | 46302 | 46303 | 46304 | 46305
項目 | 工程線名 | 開始日 | 終了日 | 日数
項目9/項目7 | A1 | 2026-09-01 | 2026-09-08 | 6
項目7/項目5 | A2 | 2026-09-09 | 2026-09-17 | 7
項目5/項目6 | A3 | 2026-09-18 | 2026-09-25 | 6
項目13/項目11 | B1 | 2026-09-02 | 2026-09-10 | 7
項目11/項目15 | B2 | 2026-09-11 | 2026-09-21 | 7
項目15/項目12 | B3 | 2026-09-22 | 2026-10-02 | 9
項目21/項目17 | C1 | 2026-09-03 | 2026-09-16 | 10
項目17/項目23 | C2 | 2026-09-17 | 2026-09-29 | 9
項目23/項目19 | C3 | 2026-09-30 | 2026-10-08 | 7
項目27/項目25 | D1 | 2026-09-01 | 2026-09-07 | 5
項目25/項目29 | D2 | 2026-09-08 | 2026-09-15 | 6
項目29/項目26 | D3 | 2026-09-16 | 2026-09-24 | 7
項目26/項目31 | D4 | 2026-09-25 | 2026-10-05 | 7
項目31/項目28 | D5 | 2026-10-06 | 2026-10-15 | 8
項目35 | E1 | 2026-09-04 | 2026-09-14 | 7
項目35/項目33 | E2 | 2026-09-15 | 2026-09-23 | 7
項目33/項目37 | E3 | 2026-09-24 | 2026-10-06 | 9
項目40 | バー1 | 2026-09-05 | 2026-09-18 | 10
項目41 | バー2 | 2026-09-07 | 2026-09-24 | 14
項目42 | バー3 | 2026-09-10 | 2026-10-01 | 16
項目43 | バー4 | 2026-09-06 | 2026-09-20 | 10
項目44 | バー5 | 2026-09-21 | 2026-10-09 | 15
項目46 | バー6 | 2026-09-12 | 2026-10-03 | 15
Formulas:
日数 = NETWORKDAYS([開始日],[終了日])

## _data (hidden)
工程ID | 工程ID | 工程線名 | 工程線の形状 | 工程線の矢印 | 実線・点線 | 工程線の太さ | 工程線の色 | 工程線の背景色 | 工程線の斜行 | 項目ID（開始日ノード） | 項目名（開始日ノード） | 開始日の行番号 | 開始日 | 開始日ノード形状 | 開始日ノードの依存タスク（行程ID、依存関係） | 開始日ノードの関係線名 | 項目ID（終了日ノード） | 項目名（終了日ノード） | 終了日の行番号 | 終了日 | 終了日ノード形状 | 終了日ノードの依存タスク（行程ID、依存関係） | 終了日ノードの関係線名 | 項目ID（中間ノード） | 中間ノード日付 | 延べ日数 | 日数 | 休日 | 調整日数 | 0.5日 | 工程削除 | 詳細工程1の名称 | 詳細工程1の協力会社 | 詳細工程1の人数 | 詳細工程1の台数 | 詳細工程1の開始日 | 詳細工程1の終了日 | 詳細工程1の延べ日数 | 詳細工程1の日数 | 詳細工程1の休日 | 詳細工程1の色 | 詳細工程1の背景色 | 詳細工程1の形状 | 詳細工程1の矢印 | 詳細工程1の備考 | 詳細工程1の表示 | 詳細工程2の名称 | 詳細工程2の協力会社 | 詳細工程2の人数 | 詳細工程2の台数 | 詳細工程2の開始日 | 詳細工程2の終了日 | 詳細工程2の延べ日数 | 詳細工程2の日数 | 詳細工程2の休日 | 詳細工程2の色 | 詳細工程2の背景色 | 詳細工程2の形状 | 詳細工程2の矢印 | 詳細工程2の備考 | 詳細工程2の表示 | 詳細工程3の名称 | 詳細工程3の協力会社 | 詳細工程3の人数 | 詳細工程3の台数 | 詳細工程3の開始日 | 詳細工程3の終了日 | 詳細工程3の延べ日数 | 詳細工程3の日数 | 詳細工程3の休日 | 詳細工程3の色 | 詳細工程3の背景色 | 詳細工程3の形状 | 詳細工程3の矢印 | 詳細工程3の備考 | 詳細工程3の表示 | 詳細工程4の名称 | 詳細工程4の協力会社 | 詳細工程4の人数 | 詳細工程4の台数 | 詳細工程4の開始日 | 詳細工程4の終了日 | 詳細工程4の延べ日数 | 詳細工程4の日数 | 詳細工程4の休日 | 詳細工程4の色 | 詳細工程4の背景色 | 詳細工程4の形状 | 詳細工程4の矢印 | 詳細工程4の備考 | 詳細工程4の表示 | 詳細工程5の名称 | 詳細工程5の協力会社 | 詳細工程5の人数 | 詳細工程5の台数 | 詳細工程5の開始日 | 詳細工程5の終了日 | 詳細工程5の延べ日数 | 詳細工程5の日数 | 詳細工程5の休日 | 詳細工程5の色 | 詳細工程5の背景色 | 詳細工程5の形状 | 詳細工程5の矢印 | 詳細工程5の備考 | 詳細工程5の表示 | 詳細工程6の名称 | 詳細工程6の協力会社 | 詳細工程6の人数 | 詳細工程6の台数 | 詳細工程6の開始日 | 詳細工程6の終了日 | 詳細工程6の延べ日数 | 詳細工程6の日数 | 詳細工程6の休日 | 詳細工程6の色 | 詳細工程6の背景色 | 詳細工程6の形状 | 詳細工程6の矢印 | 詳細工程6の備考 | 詳細工程6の表示 | 備考 | 作成日時 | 更新日時 | _meta
P0001 | P0001 | [{"id":"L0001","name":"A1","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"L"}] | yElbow | arrow |  |  | #1f77b4 |  |  | nA0 | 項目9 | 9 | 2026-09-01T00:00:00+09:00 |  |  | 関係１ | nA1 | 項目7 | 7 | 2026-09-08T23:59:59+09:00 | [5 empty] | 8 | 6 | 2 | 0 | [95 empty] | projectId | PRJ-0001
P0002 | P0002 | [{"id":"L0002","name":"A2","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | yElbow | arrow |  |  | #1f77b4 |  |  | nA1 | 項目7 | 7 | 2026-09-09T00:00:00+09:00 |  |  |  | nA2 | 項目5 | 5 | 2026-09-17T23:59:59+09:00 | [5 empty] | 9 | 7 | 2 | 0 | [95 empty] | scheduleId | SCH-0001
P0003 | P0003 | [{"id":"L0003","name":"A3","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | yElbow | arrow |  |  | #1f77b4 |  |  | nA2 | 項目5 | 5 | 2026-09-18T00:00:00+09:00 |  | [{"id":"P0002","dependency":"FS"}] |  | nA3 | 項目6 | 6 | 2026-09-25T23:59:59+09:00 | [5 empty] | 8 | 6 | 2 | 0 | [95 empty] | period | 2026/09/01-2026/11/30
P0004 | P0004 | [{"id":"L0004","name":"B1","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | xElbow | arrow |  |  | #d62728 |  |  | nB0 | 項目13 | 13 | 2026-09-02T00:00:00+09:00 |  |  | 関係１ | nB1 | 項目11 | 11 | 2026-09-10T23:59:59+09:00 | [5 empty] | 9 | 7 | 2 | 0 | [95 empty] | updatedAt | 2026-08-28T10:24:11+09:00
P0005 | P0005 | [{"id":"L0005","name":"B2","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | xElbow | arrow |  |  | #d62728 |  | true | nB1 | 項目11 | 11 | 2026-09-11T00:00:00+09:00 |  |  |  | nB2 | 項目15 | 15 | 2026-09-21T23:59:59+09:00 | [5 empty] | 11 | 7 | 4 | 0 | [95 empty] | userId | U-0001
P0006 | P0006 | [{"id":"L0006","name":"B3","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | xElbow | arrow |  |  | #d62728 |  |  | nB2 | 項目15 | 15 | 2026-09-22T00:00:00+09:00 |  |  |  | nB3 | 項目12 | 12 | 2026-10-02T23:59:59+09:00 | [5 empty] | 11 | 9 | 2 | 0 | [95 empty] | userName | 監督 太郎
P0007 | P0007 | [{"id":"L0007","name":"C1","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | crank | arrow |  | 2.5 | #2ca02c |  |  | nC0 | 項目21 | 21 | 2026-09-03T00:00:00+09:00 |  |  |  | nC1 | 項目17 | 17 | 2026-09-16T23:59:59+09:00 |  |  |  | nC9 | 2026-09-09T00:00:00+09:00 | 14 | 10 | 4 | 0 | [95 empty] | version | 12
P0008 | P0008 | [{"id":"L0008","name":"C2","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | crank | arrow |  |  | #2ca02c |  |  | nC1 | 項目17 | 17 | 2026-09-17T00:00:00+09:00 |  |  |  | nC2 | 項目23 | 23 | 2026-09-29T23:59:59+09:00 |  |  |  | nC8 | 2026-09-23T00:00:00+09:00 | 13 | 9 | 4 | 0 | [95 empty] | displayStart | 2026/09/01
P0009 | P0009 | [{"id":"L0009","name":"C3","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | crank | none |  |  | #2ca02c |  | true | nC2 | 項目23 | 23 | 2026-09-30T00:00:00+09:00 |  |  |  | nC3 | 項目19 | 19 | 2026-10-08T23:59:59+09:00 | [5 empty] | 9 | 7 | 2 | 0 | [95 empty] | displayEnd | 2026/10/10
P0010 | P0010 | [{"id":"L0010","name":"D1","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | gate | arrow |  |  | #9467bd |  |  | nD0 | 項目27 | 27 | 2026-09-01T00:00:00+09:00 |  |  |  | nD1 | 項目25 | 25 | 2026-09-07T23:59:59+09:00 |  |  |  | nD9 | 2026-09-04T00:00:00+09:00 | 7 | 5 | 2 | 0 | [95 empty] | sourceName | 代替サンプル工程表.csv
P0011 | P0011 | [{"id":"L0011","name":"D2","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | gate | arrow |  |  | #9467bd |  |  | nD1 | 項目25 | 25 | 2026-09-08T00:00:00+09:00 |  |  |  | nD2 | 項目29 | 29 | 2026-09-15T23:59:59+09:00 | [5 empty] | 8 | 6 | 2 | 0
P0012 | P0012 | [{"id":"L0012","name":"D3","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | gate | arrow |  |  | #9467bd |  |  | nD2 | 項目29 | 29 | 2026-09-16T00:00:00+09:00 |  |  |  | nD3 | 項目26 | 26 | 2026-09-24T23:59:59+09:00 | [5 empty] | 9 | 7 | 2 | 0
P0013 | P0013 | [{"id":"L0013","name":"D4","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | gate | arrow |  |  | #9467bd |  |  | nD3 | 項目26 | 26 | 2026-09-25T00:00:00+09:00 |  |  |  | nD4 | 項目31 | 31 | 2026-10-05T23:59:59+09:00 |  |  |  | nD8 | 2026-09-30T00:00:00+09:00 | 11 | 7 | 4 | 0
P0014 | P0014 | [{"id":"L0014","name":"D5","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | gate | none |  |  | #9467bd |  |  | nD4 | 項目31 | 31 | 2026-10-06T00:00:00+09:00 |  |  |  | nD5 | 項目28 | 28 | 2026-10-15T23:59:59+09:00 |  |  |  | nD7 | 2026-10-10T00:00:00+09:00 | 10 | 8 | 2 | 0
P0015 | P0015 | [{"id":"L0015","name":"E1","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | straight | arrow |  | 1 | #ff7f0e |  |  | nE0 | 項目35 | 35 | 2026-09-04T00:00:00+09:00 |  |  |  | nE1 | 項目35 | 35 | 2026-09-14T23:59:59+09:00 | [5 empty] | 11 | 7 | 4 | 0
P0016 | P0016 | [{"id":"L0016","name":"E2","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | straight | arrow |  |  | #ff7f0e |  |  | nE1 | 項目35 | 35 | 2026-09-15T00:00:00+09:00 |  |  |  | nE2 | 項目33 | 33 | 2026-09-23T23:59:59+09:00 | [5 empty] | 9 | 7 | 2 | 0
P0017 | P0017 | [{"id":"L0017","name":"E3","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | straight | arrow |  |  | #ff7f0e |  |  | nE2 | 項目33 | 33 | 2026-09-24T00:00:00+09:00 |  |  |  | nE3 | 項目37 | 37 | 2026-10-06T23:59:59+09:00 | [5 empty] | 13 | 9 | 4 | 0
P0018 | P0018 | [{"id":"L0018","name":"バー1","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"S"}] | boxS | arrow |  |  | #8c564b | #f2e3df |  | nF1 | 項目40 | 40 | 2026-09-05T00:00:00+09:00 |  |  |  | nF1e | 項目40 | 40 | 2026-09-18T23:59:59+09:00 | [5 empty] | 14 | 10 | 4 | 0
P0019 | P0019 | [{"id":"L0019","name":"バー2","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | boxM | arrow |  | 2.5 | #8c564b | #f2e3df |  | nF2 | 項目41 | 41 | 2026-09-07T00:00:00+09:00 |  |  |  | nF2e | 項目41 | 41 | 2026-09-24T23:59:59+09:00 | [5 empty] | 18 | 14 | 4 | 0
P0020 | P0020 | [{"id":"L0020","name":"バー3","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"L"}] | boxL | arrow |  |  | #8c564b | #f2e3df |  | nF3 | 項目42 | 42 | 2026-09-10T00:00:00+09:00 |  |  |  | nF3e | 項目42 | 42 | 2026-10-01T23:59:59+09:00 | [5 empty] | 22 | 16 | 6 | 0
P0021 | P0021 | [{"id":"L0021","name":"バー4","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | barAutoAdjust | arrow |  |  | #17becf | #17becf |  | nF4 | 項目43 | 43 | 2026-09-06T00:00:00+09:00 | none |  |  | nF4e | 項目43 | 43 | 2026-09-20T23:59:59+09:00 | none |  |  |  |  | 15 | 10 | 5 | 0
P0022 | P0022 | [{"id":"L0022","name":"バー5","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | barAutoAdjust | arrow |  |  | #17becf | #7fdbe7 |  | nF5 | 項目44 | 44 | 2026-09-21T00:00:00+09:00 | none |  |  | nF5e | 項目44 | 44 | 2026-10-09T23:59:59+09:00 | none |  |  |  |  | 19 | 15 | 4 | 0
P0023 | P0023 | [{"id":"L0023","name":"バー6","nameAlignment":"center","nameBold":"","nameColor":"","namePosition":"top","namePositionCoefficient":"0","namePositionWithinOptions":"","nameWritingMode":"horizontal-tb","showContentsDaysWithLineBreak":"false","showLeaderLine":"false","showNameOnLine":"true","showTotalDays":"false","showWorkingDays":"false","textSize":"M"}] | barProcessNameAdjust | arrow |  |  | #e377c2 |  |  | nF6 | 項目46 | 46 | 2026-09-12T00:00:00+09:00 | none |  |  | nF6e | 項目46 | 46 | 2026-10-03T23:59:59+09:00 | none |  |  |  |  | 22 | 15 | 7 | 0

## 使い方
この工程表の直しかた
1. シート「T10_Layout」を開きます。
2. 直せるのは C 列「開始日」と D 列「終了日」だけです。ほかのセルは保護されていて編集できません。
3. 日付は 工程表の期間（2026/09/01 〜 2026/11/30）の中で入れてください。
4. 終了日はその日を含みます（終了日当日まで作業する、という意味です）。
5. 色の帯は C・D の日付から自動で引き直されます。帯を直接ぬる必要はありません。
6. 行の追加・削除、並べ替え、シート名の変更はしないでください。取り込みができなくなります。
7. 直し終えたら、このファイルをそのまま返送してください。
※ E 列「日数」は土日を除いた日数の目安です（NETWORKDAYS）。祝日は考慮していません。
※ シート「_data」は取り込み用の控えです。非表示のままにしてください。